## RACI Matrix Template
RACI Matrix Template
R | RESPONSIBLE: Person(s) responsible for doing the work | Leadership Team |  |  |  | Project Team |  |  |  | External Resources
A | ACCOUNTABLE: Person accountable for signing off the work (max. 1) | DG | JR | Whole Team | DS | KG | NR | AAP | CF | BP | AJ | SD | SP
C | CONSULTED: Person consulted before and during task
I | INFORMED: Person informed of work progress/completion
Work Area | Task Description
Reporting | Report project status each Friday | A | I | I | bar: DS to Project Team NR
| Report risks monthly | A | bar: DS to Project Team AAP
| Report on external progress |  |  |  | Project Team CF: A/C; External Resources BP: R; External Resources AJ: R
Planning | Create launch plan |  |  | A | bar: Project Team KG to External Resources SP
| Create rollback plan | C | C | A | bar: Project Team KG to Project Team CF
Execution | Build all deliverables | C | I | bar: DS to Project Team NR
| Setup test environment | C |  |  | DS: A/C; Project Team NR: R; Project Team AAP: R; Project Team CF: C
| Setup live environment |  |  |  | DS: A/C; Project Team KG: R; Project Team NR: R; Project Team AAP: R; Project Team CF: C